## Executive Summary
Technopolis Constructions - Solitaire Unity
AI Real-Estate Calling Pipeline - Debugging & Fix Report
Project: | Technopolis AI Calling Console (Vernika / sales_1)
Generated: | 2026-08-14
Environment: | Local (Windows) + VPS (srv1732329.hstgr.cloud, Docker + PostgreSQL)
Total Bugs Found & Fixed: | 14
Critical (blocked dialing/transcripts): | 6
Medium (broken features): | 4
Low (drift / dormant / cosmetic): | 4
Billing Blocker (not code): | 1
Total Files Changed (this session): | 60+
Overall Status: | ALL FIXED & DEPLOYED - VPS healthy, calls stopped, ready to dial
Remaining Blocker: | Gemini prepayment credits depleted - top up in AI Studio
Round 2 (PostgreSQL migration + 3-agent audit) | 27 bugs found & fixed; full suite 51/51 green on PostgreSQL; app boots with 151 routes; weekly ZIP + migration + DNC verified end-to-end
Round 3 (frontend funnel + Vobiz plug-and-play + digital 2-concurrency) | 5 items fixed; suite 55/55 green; funnel+Vobiz card deployed to VPS
Round 4 (KPI honesty + Vobiz extras/webhooks + funnel nav + prompt chain + campaign enforcement + Hermes watchdog) | 6 items fixed; suite 61/61 green; watchdog cron live on VPS every 5 min with TTS
Round 5 (live dialing status + broker source filter + chart layout + real KPI trends + watchdog runner) | 5 items fixed; suite 63/63 green; V7 deployed
Round 6 (pre-recorded greeting plays + Gemini S2S + Telugu primary + transcription fixed) | 5 items fixed; suite 64/64 green; V8 deployed; language=te-IN mirror=ON

## Bug Log
# | Area | Bug / Issue | Severity | Root Cause | Solution / Fix Applied | Files Changed | Time Taken (est.) | Status | Verified On
1 | Transcription | Summary/analysis generates but raw TRANSCRIPT text is empty in dashboard | CRITICAL | GEMINI_TRANSCRIPTION_MODEL was set to gemini-3.1-flash-lite (audio unsupported) -> transcribe_audio returned None; transcript lives only in JSONL never DB; dashboard _transcript returned [] (truthy in JS so frontend never fetched API) | Set model to gemini-2.5-flash in .env + config default; fixed manual transcribe route (camelCase inlineData, header auth, configured model); dashboard _transcript resolves real JSONL; MIN_TRANSCRIBE_SEC 15->5; relaxed hybrid audio guard | backend/.env, backend/config.py, backend/services/transcriber.py, backend/api/routes/console_api.py, backend/api/routes/dashboard.py, backend/services/transcript_hybrid.py, frontend/static/js/restored.js, app.js, voice_test.html | ~45 min | FIXED | VPS container (gemini-2.5-flash confirmed)
2 | Dashboard / SQL | /api/campaign/state returned 500: 'operator does not exist: text = integer' | CRITICAL | json_extract(extra,'$.inbound_interest') = 1 - Postgres returns text via ->> so comparing text to integer fails | Added CAST(json_extract(...) AS INTEGER) = 1 at all 4 sites in storage.py + 3 in CLI scripts | backend/core/storage.py, backend/scripts/cleanup_fake_outcomes.py, backend/scripts/audit_site_visits_all.py | ~20 min | FIXED | VPS (/api/campaign/state now 200)
3 | Orchestration / Dialer | Start Campaign never dialed - all leads stayed pending | CRITICAL | worker.py dial gate: `if not acquire_phone_slot()` - acquire_phone_slot returns None, so `not None` always True -> returned 'Line busy' without calling Vobiz | Changed gate to `if phone_is_busy(v_from)` then acquire_phone_slot; also fixed psycopg2 % placeholder crash in db.py (bare % -> %%) | backend/core/worker.py, backend/core/db.py | ~30 min | FIXED | VPS (orchestration dial line reached, actual Vobiz call)
4 | Campaign List | Uploaded campaigns never appear in 'New outbound campaign' list (shows 'No campaigns uploaded yet') | CRITICAL | storage.py _get_campaign_sources_sync used SELECT alias src_name in WHERE - Postgres rejects column alias in WHERE -> endpoint 500 -> frontend rendered empty | Repeated json_extract(extra,'$.upload_source') expression in WHERE/GROUP BY instead of alias (SQLite + PG compatible) | backend/core/storage.py | ~20 min | FIXED | VPS (/api/campaign/sources now 200)
5 | Call Connectivity | Incoming call drops ~1 second after pickup | BLOCKER (billing) | Gemini Live WS opens, setup accepted, then Google closes with 1011 'Your prepayment credits are depleted' (429 RESOURCE_EXHAUSTED). Not a code/model bug | Config already correct (models/gemini-3.1-flash-live-preview, Aoede, en-IN). FIX = top up prepayment credits in Google AI Studio. Call fails cleanly by design rather than 180s dead air | None (config verified correct) | ~25 min | NEEDS BILLING | VPS logs show 1011 credits message
6 | Storage / API | update_lead_info ImportError at runtime (email auto-send + inbound finalize aborted) | HIGH | worker.py:2632/3257/3263 import core.storage.update_lead_info which did not exist | Added async update_lead_info(lead_id, *, name=None, email=None) + _update_lead_info_sync to storage.py | backend/core/storage.py | ~15 min | FIXED | py_compile + import verified
7 | Health Agent (RAG) | RAG Keeper heal never rebuilt kb_chunks.json (reported healed=True always) | MEDIUM | rag_agent heal called build_chunks_from_rag('sales_1') but that function expects raw KB text and only main() writes to disk | Heal now fetches get_role_rag_source_text, chunks it, writes data/sales_1/kb_chunks.json in the same schema main() uses | backend/services/health_agents/agents/rag_agent.py | ~15 min | FIXED | py_compile + heal output verified
8 | Number Allocator | P1-P9 numbers configured in console UI had no effect on orchestrator | MEDIUM | configured_pools() iterated _ROLES.values() but _ROLES is a tuple -> AttributeError swallowed by except: pass | Iterate _ROLES (tuple) correctly, fetch state per role, merge P1-P9 when non-empty; env fallback intact | backend/core/number_allocator.py | ~20 min | FIXED | configured_pools() no longer raises
9 | Voice / Persona | AI sounded like aggressive Jordan Belfort 'closer', not natural Indian female | MEDIUM (UX) | Prompt pushed 'top-tier closer / Straight Line / CERTAINTY IS EVERYTHING'; voice Sulafat vs addon mismatch; temp 0.86 | Rewrote prompt to calm Hyderabadi/Bengaluru Indian female relationship consultant; voice=Aoede (unified), temp=0.65, en-IN languageCode on all paths, added Indian pronunciation examples | backend/prompts/sales_1_prompt.txt, backend/config.py, backend/.env, backend/services/vobiz_bridge/turn_taking_addon.py | ~40 min | FIXED | grep confirms no Belfort hype left
10 | Memory / Continuity | Per-lead memory (lead_memory) only injected on orchestration dials, not manual/incoming/callback | MEDIUM | _lead_memory_text only attached in _process_single_lead; other legs relied only on analysis history | Added _persist_lead_memory writer (campaign + manual + incoming legs) and _build_continuity_memory_block injected into history_block on every WS connect path | backend/core/worker.py, backend/services/vobiz_bridge/live_session.py | ~40 min | FIXED | code trace verified all paths
11 | Watchdog | VPS self-healing watchdog dead for hours (systemd timer 203/EXEC every tick) | HIGH (ops) | watchdog script lost execute bit (-rw-rw-rw-) | chmod +x technopoliss-watchdog.sh; dry-run tick passes; timer active; service exits 0 | watchdog/technopoliss-watchdog.sh (chmod on VPS) | ~10 min | FIXED | VPS log shows TICK begin/end
12 | Frontend | Transcript modal crashed when lead.transcript was an array [] (truthy) or a string | MEDIUM | restored.js treated [].split as string -> TypeError; root app.js lead.transcript.forEach on string -> TypeError; voice_test.html CSS 404 | Handle string / empty-string / array safely; String(rawText¦¦''); fixed /static/css/styles.css path | frontend/static/js/restored.js, app.js, frontend/templates/voice_test.html | ~20 min | FIXED | node --check + parse pass
13 | Legacy / Branding | Surya Developers, Data Edge, Sales 2, Channel Partner, Priya, sellers/buyers still in code/data | MEDIUM (cleanup) | Full product consolidation to single role sales_1 left legacy roles/brands in code, env, prompts, greetings, DB | Purged legacy roles/brands across backend + frontend + .env + prompts; renamed prompts/priya.py->role_prompts.py; single RAG + single greeting PCM; migrated vernikaai DB leads to sales_1 | 60+ files across backend/ and frontend/ | ~3 hrs (multiple agents) | FIXED | zero legacy token hits repo-wide
14 | Clear Data / Wipe | Clicking Clear Data didn't clear dashboard data (frontend-backend not synced) | MEDIUM | Root dashboard campaignControlClear only reloaded campaigns, not real leads/KPIs; dashboard /leads fetched ALL roles (incl. legacy vernikaai) | campaignControlClear now clears appState + reloads real leads + updateDashboardUI + campaigns; /leads + /overview role-scoped to sales_1; loadRealLeads passes role | app.js, backend/api/routes/dashboard.py | ~25 min | FIXED | VPS endpoints 200, role-scoped
15 | Database / Core | App was PostgreSQL-only with NO local/dev fallback: default DSN host 'postgres' never resolves outside docker, so local dev, CI and the whole test suite crashed at startup (RuntimeError: could not translate host name 'postgres'). Plan requires 'PostgreSQL (production) and SQLite (development fallback)'. | CRITICAL | core/db.py default_dsn() hard-coded host='postgres' (docker network alias) as the default for every environment; docker-compose never passed PGHOST explicitly. | default_dsn() now defaults to localhost; docker-compose sets PGHOST=postgres + PG* creds explicitly for the container. Tests now run against a dedicated technopoliss_test Postgres DB (tests/helpers.py) via the real production storage path. | backend/core/db.py, docker-compose.yml, backend/tests/helpers.py, backend/tests/test_orchestration.py, backend/tests/test_audit_fixes_smoke.py, backend/tests/test_digital_excel_ingest.py | ~15-40 min | FIXED | 2026-08-14 (PostgreSQL + parallel agent audit)
16 | Core / Lead Memory | lead_memory.get_memory crashed on Postgres: positional fallback row[2] grabbed last_interaction_at (float) instead of summary (index 1) because DictRow is not sqlite3.Row — every memory read raised AttributeError: 'float' object has no attribute 'strip'. Memory-aware dials (plan Phase 5) were broken on the real DB. | CRITICAL | Positional index fallback assumed row[2]=summary; SELECT order is facts_json(0), summary(1), last_interaction_at(2), version(3). Only masked on Postgres shim (DictRow). | Rewrote get_memory with name-first accessor + correct positional fallback (summary=1, version=3). | backend/core/lead_memory.py | ~15-40 min | FIXED | 2026-08-14 (PostgreSQL + parallel agent audit)
17 | WhatsApp / Orchestration | live_job_executor.execute_whatsapp_job wrote datetime('now') (-> now(), a timestamptz) into leads.whatsapp_sent_at REAL column -> DatatypeMismatch on Postgres; the bare except: pass swallowed it, so the brochure send was recorded as never-sent (whatsapp_sent stayed 0) and duplicate brochures could be sent. | HIGH | REAL (epoch) timestamp column assigned a timestamptz via the SQL translation layer; also `import time` was missing so the replacement raised NameError, also swallowed. | Store epoch seconds (time.time()) as a parameter like every other REAL timestamp column; added the missing import. | backend/core/live_job_executor.py | ~15-40 min | FIXED | 2026-08-14 (PostgreSQL + parallel agent audit)
18 | Orchestration / Concurrency | workflow_queue.claim_next was not atomic under concurrency: SELECT then UPDATE in READ COMMITTED let two workers both pass the lead-lock NOT EXISTS check and claim the same job (or two jobs of one lead) — duplicate dials (plan Phase 4 SKIP LOCKED requirement violated). | HIGH | Two-statement claim without FOR UPDATE / SKIP LOCKED; lead row never locked. | Postgres path now selects with FOR UPDATE OF j, l SKIP LOCKED inside the claim transaction and claims with a conditional UPDATE (rowcount check); added _unclaim + number_resolver for atomic claim+line assignment. Added 5 concurrency tests. | backend/core/workflow_queue.py, backend/core/orchestration_dispatcher.py | ~15-40 min | FIXED | 2026-08-14 (PostgreSQL + parallel agent audit)
19 | Orchestration / Routing | Callbacks rang from the WRONG originating line: dispatcher peeked lead source with a separate SELECT, then claimed whatever job won the race — a digital callback could ring from P1/P2 cold line. | HIGH | Line chosen before claim; not resolved from the actually-claimed job. | Added _job_lead_source + number_resolver passed into claim_next so the callback line (P1/P2 cold, P3 digital) is resolved from the claimed job inside the same transaction; dispatcher re-checks line lock/cooldown post-claim. | backend/core/orchestration_dispatcher.py, backend/core/workflow_queue.py | ~15-40 min | FIXED | 2026-08-14 (PostgreSQL + parallel agent audit)
20 | Orchestration | PRIORITY dict missing JobType.SITE_VISIT_RESCHEDULE -> KeyError crashed any site-visit reschedule at scheduling time, breaking the reschedule lifecycle. | HIGH | New job type added to enum but not to the priority table. | Added SITE_VISIT_RESCHEDULE: 4 to PRIORITY + regression test (every JobType covered). | backend/core/orchestration_service.py, backend/tests/test_audit_fixes_smoke.py | ~15-40 min | FIXED | 2026-08-14 (PostgreSQL + parallel agent audit)
21 | MCP Server | get_lead_status crashed (AttributeError: str has no .get) because leads.extra is a JSON string in the DB; create_lead only inserted a row and never enqueued a fresh_call job — the MCP tools were effectively dead for the pipeline (plan objective 1.2). | HIGH | Extra read as dict; no job enqueued on create. | _lead_extra_dict() tolerates dict or JSON string; _lead_sandbox() derives sandbox from column > stage; create_lead now normalizes phone (E.164), persists budget/location/property_type into extra, enqueues fresh_call on the correct pool; trigger_manual_call checks operator dnc_list + do_not_contact register. | backend/mcp_server.py | ~15-40 min | FIXED | 2026-08-14 (PostgreSQL + parallel agent audit)
22 | API / DND Compliance | create_callback (api/routes/callbacks.py) had no DNC enforcement — an operator could schedule a callback for an opted-out number (plan 1.4/4.3 compliance gap). | HIGH | Missing do_not_contact lookup before scheduling. | create_callback now returns HTTP 409 'number is on the do-not-contact list' before scheduling. | backend/api/routes/callbacks.py | ~15-40 min | FIXED | 2026-08-14 (PostgreSQL + parallel agent audit)
23 | Orchestration / Dashboard | leads.sandbox column never updated by the event engine: failed calls never moved to SB2, callbacks never returned to SB1, interested leads never entered SB3 — dashboard sandbox views were wrong. | MEDIUM | Event-to-job functions mutated lifecycle_status but not the sandbox column. | _set_sandbox() helper wired into failed_call->SB2, schedule_callback->SB1, interested/whatsapp_package_sent->SB3; sandbox_for_stage(CALLBACK_REQUESTED) corrected to SB1 per plan flowchart. Added 4 sandbox-flow tests. | backend/core/orchestration_service.py, backend/core/workflow_models.py, backend/tests/test_audit_fixes_smoke.py | ~15-40 min | FIXED | 2026-08-14 (PostgreSQL + parallel agent audit)
24 | Voice / TTS | gemini_tts.py used httpx.Optional[...] (httpx has no Optional attr) — pyflakes undefined names; latent import-time failure under type evaluation. | HIGH | Invalid attribute access in annotations. | Replaced with Optional[httpx.AsyncClient] / Optional[httpx.Response] using typing.Optional. | backend/services/gemini_tts.py | ~15-40 min | FIXED | 2026-08-14 (PostgreSQL + parallel agent audit)
25 | Voice / Routes | web_voice.py /ws/voice-test called handle_browser_voice_ws which was never imported -> NameError 500 on the browser voice test path (plan Section 4 manual test). | HIGH | Missing import. | Added from services.browser_voice_bridge import handle_browser_voice_ws. | backend/api/routes/web_voice.py | ~15-40 min | FIXED | 2026-08-14 (PostgreSQL + parallel agent audit)
26 | Voice / Routes | factory.py sandbox routes referenced create_agent/list_agents/etc. (undefined) -> NameError on every /api/factory route (now correctly unmounted legacy; imports fixed so it parses). | HIGH | Missing imports from services.sandbox_manager. | Added the full sandbox_manager import set. | backend/api/routes/factory.py | ~15-40 min | FIXED | 2026-08-14 (PostgreSQL + parallel agent audit)
27 | API / Routes | console_api.py virtual-meet endpoints called undefined extract_role(request) -> NameError; virtual meet capture/reschedule could never be read. | MEDIUM | Helper never defined in the module. | Added module-level extract_role (query param > X-User-Role/X-Role header > sales_1). | backend/api/routes/console_api.py | ~15-40 min | FIXED | 2026-08-14 (PostgreSQL + parallel agent audit)
28 | DNC / Compliance | core/dnc.py used SQLite-only INSERT OR IGNORE into a private dnc_list table while the queue/dispatcher check do_not_contact — operator opt-outs were silently never recorded (TRAI/DND broken) and the two registers diverged. | HIGH | dnc.py predated the do_not_contact canonical table; INSERT OR IGNORE invalid on Postgres (swallowed by except). | Rewrote dnc.py against the canonical do_not_contact(normalized_phone) table with ON CONFLICT DO UPDATE; add_to_dnc and opt_out now share one register; is_phone_blocked checks it (suffix + exact). Verified add/check/opt-out round trip on Postgres. | backend/core/dnc.py | ~15-40 min | FIXED | 2026-08-14 (PostgreSQL + parallel agent audit)
29 | Voice / Dialer | _process_single_lead (orchestration dial leg) had no DNC guard — an opt-out landing between job creation and execution would still be dialed. | MEDIUM | Guard existed in campaign sub-workers but not the orchestration entry point. | Added is_phone_blocked check before marking dialing; returns dnc_blocked outcome without dialing. | backend/core/worker.py | ~15-40 min | FIXED | 2026-08-14 (PostgreSQL + parallel agent audit)
30 | Voice / Live Session | live_session.py: _activity_end_nudge_seq read/incremented in a nested Gemini handler without nonlocal -> UnboundLocalError ('referenced before assignment') during activity-end nudges. | HIGH | Missing nonlocal declaration for the enclosing-scope counter. | Added _activity_end_nudge_seq to the pump_gemini_to_queue nonlocal list. | backend/services/vobiz_bridge/live_session.py | ~15-40 min | FIXED | 2026-08-14 (PostgreSQL + parallel agent audit)
31 | Voice / Opening | build_opening_line ignored row_data entirely — every call got the static greeting even when the lead name/company was available. | LOW | Interpolation helpers existed but were unused. | Interpolate name + company via the existing helpers (fallback stays packaged line). | backend/core/opening_line.py | ~15-40 min | FIXED | 2026-08-14 (PostgreSQL + parallel agent audit)
32 | Ops / Weekly ZIP | weekly_zip_archive.py used a trailing 7-day window at runtime and never pruned originals — a Monday 6 AM run captured the current week instead of the PRIOR calendar week (plan Phase 7 violated). | HIGH | mtime >= now-7d window; no prune step. | Prior-calendar-week [Mon, Mon) bounds in Asia/Kolkata; prunes archived originals after a successful zip; dry_run flag; verified end-to-end with a temp recordings dir (zip contains only prior-week files). | backend/scripts/weekly_zip_archive.py | ~15-40 min | FIXED | 2026-08-14 (PostgreSQL + parallel agent audit)
33 | Callbacks / Scheduler | callback_schedule.resolve_callback_epoch relative branch ('in 10 minutes') never shifted into the 11:00-19:30 IST window — a 7:35 PM callback was scheduled inside quiet hours (plan Phase 3). | HIGH | Relative targets computed as now+delta with no window slide. | Added _slide_into_working_hours: before-day -> 11:00 same day, after 19:30 -> next day 11:00; applied to relative + fallback branches; absolute times untouched. Verified 19:25+10min -> next day 11:00. | backend/services/callback_schedule.py | ~15-40 min | FIXED | 2026-08-14 (PostgreSQL + parallel agent audit)
34 | WhatsApp / Blue Loop | WhatsApp 'not interested again' was never handled: _classify_inbound_reply returned ('','') so the Blue Loop never reached terminal LOST/DNC (plan Phase 6). | HIGH | Not-interested phrases filtered out before classification. | Returns ('not_interested','whatsapp'); process_campaign_whatsapp_reply now calls orchestration opt_out (lead -> opted_out/LOST, jobs cancelled, do_not_contact row) and publishes lead_updated. | backend/services/whatsapp_leads.py | ~15-40 min | FIXED | 2026-08-14 (PostgreSQL + parallel agent audit)
35 | WhatsApp / Direct Booking | Direct-booking bypass (willing-to-visit -> Site Visit + cancel nudges) only ran AFTER a successful Gemini call — with no API key or on API failure the lead was never transitioned (plan Phase 6 bypass broken). | HIGH | Keyword logic inside the Gemini success path only. | Deterministic _detect_site_visit_intent + async _apply_site_visit_bypass run BEFORE Gemini (negation-aware); cancels whatsapp_followup_24h + interested_followup jobs; verified. | backend/services/whatsapp_conversation.py | ~15-40 min | FIXED | 2026-08-14 (PostgreSQL + parallel agent audit)
36 | WhatsApp / Webhook | Meta webhook had no idempotency on wa_message_id — retried deliveries caused duplicate lead updates + duplicate AI replies. | MEDIUM | No dedup tracking. | Thread-safe bounded LRU _MessageIdCache keyed on wa_message_id; seen ids short-circuit with dedup:true. Ingest exceptions now mark ignored so the AI reply step is skipped. | backend/api/routes/whatsapp.py | ~15-40 min | FIXED | 2026-08-14 (PostgreSQL + parallel agent audit)
37 | WhatsApp / Workflow | On INTERESTED only a greeting text was sent; the brochure depended solely on the durable whatsapp_package job — a down/backlogged job loop meant no brochure (plan Phase 6 'WhatsApp Immediate Brochure'). | MEDIUM | Brochure deferred to the job executor only. | send_full_package also called inline on the INTERESTED transition (guarded try/except), keeping the durable job as source of truth. | backend/services/whatsapp/workflow.py | ~15-40 min | FIXED | 2026-08-14 (PostgreSQL + parallel agent audit)
38 | WhatsApp / NLP | classify_reply marked any message with a VISIT keyword as interested even when negated ('we are NOT interested in a visit'); plain 'no' also killed following positive intent. | LOW | Keyword ordering without negation awareness. | Added NEGATED_VISIT_PHRASES (checked first) and POSITIVE_VISIT_PHRASES (checked before the generic no); verified 9 classification cases. | backend/services/whatsapp/templates.py | ~15-40 min | FIXED | 2026-08-14 (PostgreSQL + parallel agent audit)
39 | Frontend / Dashboard | KPI cards, donut and hourly charts filtered by appState.currentSandbox while the leads table used currentSandboxFilter — switching sandbox updated only the table, leaving charts/KPIs stale (plan Section 4 manual check #2). | HIGH | Two divergent sandbox selection variables. | setSandboxFilter now also sets appState.currentSandbox and refreshes dashboard stats; calculateKpis + 4 chart sites aggregate when sandbox==0 (all). | app.js | ~15-40 min | FIXED | 2026-08-14 (PostgreSQL + parallel agent audit)
40 | Ops / Watchdog | VPS watchdog monitored backend/openwa/caddy but NOT the PostgreSQL container, and still ran obsolete SQLite WAL repair — a Postgres outage would silently kill the whole pipeline with no auto-recovery. | HIGH | Watchdog predated the Postgres migration. | Added SVC_POSTGRES/CT_POSTGRES to container run+health checks; new pg_health_check() (pg_isready + restart); SQLite repair kept as guarded legacy no-op. | watchdog/technopoliss-watchdog.sh | ~15-40 min | FIXED | 2026-08-14 (PostgreSQL + parallel agent audit)
41 | Tests | New working-hours test from agent audit had miscalculated expectations (Aug 5 18:00 vs correct Aug 4 14:30 for +12 working hours; Aug 7 18:00 vs correct Aug 7 13:00 for +24h). | MEDIUM | Hand arithmetic error in the test, not the code (code verified correct). | Corrected expectations to match 8.5h/day (11:00-19:30) working-hours math; suite green. | backend/tests/test_orchestration.py | ~15-40 min | FIXED | 2026-08-14 (PostgreSQL + parallel agent audit)
42 | API / Dashboard | GET /api/orchestration/kpis crashed with IndexError (500). PostgreSQL RealDictCursor collapses un-aliased aggregate columns: three SUM(CASE...) columns are all named 'sum' so the dict ends with only {'count', 'sum'} and attempts[2]/attempts[3] index out of range. Same latent bug in /api/orchestration/numbers and /api/sandbox/overview (the latter silently returned all-zero aggregates because its try/except swallowed the IndexError). | HIGH | RealDictCursor dedupes duplicate column names; positional access then indexes a shorter dict. | Added explicit AS aliases (total_attempts/retry_2/retry_3/failed_attempts, answered_calls/failed_calls/last_used_at, distinct_leads/total_jobs/completed_jobs/active_jobs) to every un-aliased aggregate query in the two route files. Added 2 regression tests (54/54 suite green). | backend/api/routes/orchestration.py, backend/api/routes/sandbox_overview.py, backend/tests/test_audit_round2.py | ~20 min | FIXED | 2026-08-14 (VPS live verification, Agent B found)
43 | Frontend / Charts | Sales funnel (sandbox totals) requested as the pipeline visual. The old 'Campaign Automation Pipeline' strip (Lead Upload -> Pending -> ... -> Site Visit) used generic status buckets that did not reflect the 4-sandbox flow; the Outcome Distribution donut was temporarily replaced by a funnel in a prior pass, which the user corrected — donut must stay. | MEDIUM | Pipeline strip showed status buckets, not sandbox stages; funnel was initially placed where the donut belonged. | Kept the Outcome Distribution donut in its chart slot; replaced the Campaign Automation Pipeline strip with a 5-stage Sales Funnel (Sandbox 1 -> 2 -> 3 -> 4 -> Site Visit) with live counts (funnel-sb1..sb4 + funnel-sv) populated from calculateKpis; each stage is clickable and filters the dashboard to that sandbox via setSandboxFilter. | index.html, app.js | ~20-40 min | FIXED | 2026-08-14 (round 3: funnel/favicon/digital concurrency/Vobiz/cleanup)
44 | Frontend / Branding | No favicon on the dashboard/console browser tab (default blank icon). | LOW | No <link rel=icon> and no logo asset. | Added frontend/static/favicon.svg (Technopolis 'T' monogram on brand-red gradient) + <link rel=icon> in index.html and console.html. | frontend/static/favicon.svg (new), index.html, frontend/templates/console.html | ~20-40 min | FIXED | 2026-08-14 (round 3: funnel/favicon/digital concurrency/Vobiz/cleanup)
45 | Orchestration / Digital | Digital sub-sandbox (P3) could only dial 1 lead at a time — the busy tracker was a SET, so a second digital lead waited even though the plan requires 2 concurrent calls from P3 ('2 concurrency calls, from P3 make call to 2 leads'). | HIGH | SANDBOX1_DIGITAL pool had a single P3 entry; dispatcher tracked busy as a set (one slot per number). | SANDBOX1_DIGITAL now registers P3 twice (concurrency slot); dispatcher busy tracking changed to a count dict with capacity = pool-tuple occurrences, guarded by a threading lock so multiple workers cannot over-claim; ORCHESTRATION_WORKER_COUNT default raised 1->2 (PostgreSQL multi-writer). verify: 2 digital leads claim P3 concurrently, 3rd blocked. | backend/core/number_allocator.py, backend/core/orchestration_dispatcher.py, backend/core/orchestration_runtime.py, backend/config.py, backend/tests/test_audit_round2.py | ~20-40 min | FIXED | 2026-08-14 (round 3: funnel/favicon/digital concurrency/Vobiz/cleanup)
46 | API / Vobiz | Vobiz credentials were single-account only (one auth_id/auth_token); no way to manage multiple trunks or see the webhook/numbers from the UI — user had to edit backend .env for any change. | HIGH | VobizUpdate model only accepted one auth pair; no GET endpoint; numbers only in .env. | Extended VobizUpdate with accounts[] (name/auth_id/auth_token); added GET /api/settings/vobiz returning accounts, webhook URL (public /vobiz/answer), from_number, has_env_override, and P1-P9 numbers; resolve_vobiz_credentials prefers accounts[0] when stored; new Vobiz Integration card in the Configuration view: multiple auth accounts (+ Add / delete), webhook display, P1-P9 inputs saved via /api/tuning -> role_state -> configured_pools() (plug-and-play, no backend edits). | backend/api/routes/console_api.py, backend/core/vobiz_credentials.py, index.html, app.js | ~20-40 min | FIXED | 2026-08-14 (round 3: funnel/favicon/digital concurrency/Vobiz/cleanup)
47 | Repo Hygiene | Junk/unwanted files: debug-cbc88a.log (debug artifact), chrome_err.log (0-byte), nginx_technopoliss.conf (dead config, Caddy replaced it), start_all.sh (dev-only localtunnel launcher), wipe_vps.sh (executed one-time cleanup), backend/test_analysis.py (unreferenced scratch probe), __pycache__ .pyc caches at root/backend. | LOW | Accumulated during development; nginx config predates the Caddy migration. | Deleted 8 items (grep-verified unreferenced first). Kept verified-functional near-misses: backend/debug_agent_log.py (imported by worker/supervisor/audio/live_session), sandbox_config.py, frontend/digital-sheets-apps-script.js (served by ui.py), root data/call_quality.db (live data). | debug-cbc88a.log, chrome_err.log, nginx_technopoliss.conf, start_all.sh, wipe_vps.sh, backend/test_analysis.py, __pycache__/* | ~20-40 min | FIXED | 2026-08-14 (round 3: funnel/favicon/digital concurrency/Vobiz/cleanup)
48 | Frontend / KPIs | KPI cards showed fabricated trend percentages (arrow_upward 12% / 8% / 24% / 2% hardcoded in index.html) — even with zero calls the cards claimed growth. | MEDIUM | Hardcoded demo values in the KPI card markup; no delta computation. | Replaced with real 7-day deltas computed in calculateKpis (_computeKpiTrends: this week vs prior week from called_at timestamps). No baseline → shows '—' with trending_flat icon; real up/down → colored arrow with ¦Δ¦%. Never fabricates a number. | index.html, app.js | ~30-60 min | FIXED | 2026-08-14 (round 4: KPI/Vobiz/funnel/prompt chain/campaign gaps/watchdog)
49 | Vobiz / Config | Vobiz tab lacked: extra dial numbers beyond P1-P9, inbound webhook display, and phone_numbers persistence in the config API. | MEDIUM | VobizUpdate model had no phone_numbers field; GET returned only the outbound answer URL. | Added phone_numbers[] to VobizUpdate + GET /api/settings/vobiz now returns both outbound (/vobiz/answer) and inbound (/vobiz/incoming) webhooks plus stored extra numbers; get_all_outbound_numbers already consumes stored phone_numbers for round-robin. Frontend Vobiz tab: Extra Numbers list (+ Add / delete) wired into saveVobizConfig. | backend/api/routes/console_api.py, index.html, app.js | ~30-60 min | FIXED | 2026-08-14 (round 4: KPI/Vobiz/funnel/prompt chain/campaign gaps/watchdog)
50 | Frontend / Funnel | Funnel stage clicks only filtered the dashboard in place; user wanted clicking 'Sandbox 2 · Retry Engine' to OPEN that sandbox's campaign tab. | LOW | Funnel stages called setSandboxFilter(n) only. | Added window.openSandboxCampaign(n): switchView('campaigns') + selectCampaignTab(n) + toast. All 4 sandbox stages now navigate; site-visit stage keeps its filter behavior. Also fixed switchView missing view-vobiz in the hide list (would have stacked views). | app.js, index.html | ~30-60 min | FIXED | 2026-08-14 (round 4: KPI/Vobiz/funnel/prompt chain/campaign gaps/watchdog)
51 | RAG / Prompt chain | Clearing RAG in the dashboard left stale lru-cached/on-disk kb_chunks.json injected into the next call; prompt-version restore skipped KB rebuild. | HIGH | rebuild_role_kb_chunks early-returned on empty text without cache_clear/unlink; _restore_prompt_version_sync never rebuilt chunks. | rebuild_role_kb_chunks now always cache_clear() first and unlinks stale kb_chunks.json when the KB is emptied; _restore_prompt_version_sync mirrors update_tuning by rebuilding KB chunks after restore. Frontend save → role_state (DB-first) → next call uses new prompt/rag with no backend edits (verified full chain). | backend/services/chunk_rag.py, backend/core/storage.py | ~30-60 min | FIXED | 2026-08-14 (round 4: KPI/Vobiz/funnel/prompt chain/campaign gaps/watchdog)
52 | Campaign / Config | Campaign fields stored but not enforced: skip_recently_days (no claim-time filter), retry_when='same_run' (retries always anchored +24h), repeat_type/schedule_at (no auto-relaunch). | MEDIUM | Config was persisted and round-tripped but the dialer ignored three fields. | skip_recently_days: claim_next gains the param + SQL filter on leads.first_called_at (PG+SQLite), dispatcher reads campaign config (30s cache). retry_when: _schedule_failed_call_retry reads campaign config; 'same_run' retries after the inter-call delay, else keeps same-clock-time +N×24h. repeat_type: orchestration supervisor runs _auto_relaunch_repeating_campaigns every 60s — re-queues drained daily/weekly campaigns and stamps next_run_at. | backend/core/workflow_queue.py, orchestration_dispatcher.py, worker.py, orchestration_runtime.py, tests | ~30-60 min | FIXED | 2026-08-14 (round 4: KPI/Vobiz/funnel/prompt chain/campaign gaps/watchdog)
53 | Ops / Watchdog | No Hermes-driven self-healing watchdog: container/queue/glitch issues required human eyes; no TTS announcements. | MEDIUM | Only the shell systemd watchdog (restarts at 60s) existed; no agent-level diagnose/fix/TTS layer. | Created watchdog/hermes_watchdog_check.sh (byte-stable VPS health sensor: containers, /health, pg, queue depth, glitch grep, disk) + hermes_watchdog_runner.sh (SSH wrapper) + hermes_watchdog_job.md (cron prompt: monitor-mode change detection, safe-fix table, TTS announcements, escalation rules). Registered as Hermes cron 'Technopolis VPS Self-Healing Watchdog' every 5 min; live run correctly detects the ongoing Gemini 429 anomaly. | watchdog/hermes_watchdog_check.sh, hermes_watchdog_runner.sh, hermes_watchdog_job.md, cron job fae943a17488 | ~30-60 min | FIXED | 2026-08-14 (round 4: KPI/Vobiz/funnel/prompt chain/campaign gaps/watchdog)
54 | Workflow / Status | Uploaded leads stayed 'pending' in the dashboard until the Vobiz dial literally started — claimed-but-not-yet-executed leads showed pending, and the dashboard only refreshed on manual actions. | HIGH | leads.status only flipped to 'dialing' inside _process_single_lead just before make_vobiz_call (worker.py:770); claim_next never touched the leads row. Dashboard reloaded leads only on manual refresh + one-shot 2s after Start, then only polled cached campaign state. | claim_next now flips leads.status='dialing' at claim time (idempotent UPDATE where status IN pending/scheduled/ready); dashboard auto-refreshes loadRealLeads+updateDashboardUI every 3s while the campaign is active (pulse-active indicator). Regression tests: test_claimed_job_flips_lead_to_dialing, test_two_fresh_leads_claim_two_numbers_in_parallel (P1+P2 verified). | backend/core/workflow_queue.py, app.js, tests | ~30-60 min | FIXED | 2026-08-14 (round 5: dialing status / source filter / layout / trends / watchdog runner)
55 | Frontend / Filters | No way to filter leads by which broker/Excel file uploaded them; upload provenance (file name / broker_id) was not exposed by the dashboard API. | MEDIUM | GET /api/dashboard/leads omitted upload_source/broker_id/extra; ingest_digital_file's filename was dropped from extra by _bulk_add_leads_sync. | API now returns upload_source, broker_id, extra per lead; storage keeps provenance in extra; new Source dropdown (#filter-source, styled like existing filters) auto-populated from distinct sources (file name, 'Google Sheet broker_N', 'Manual'); Source column added to the call-logs table; filterBySource composes with sandbox + disposition filters and drives KPIs. | backend/api/routes/dashboard.py, backend/core/storage.py, index.html, app.js | ~30-60 min | FIXED | 2026-08-14 (round 5: dialing status / source filter / layout / trends / watchdog runner)
56 | Frontend / Layout | Charts layout wrong: funnel lived inside the pipeline card, timeline shared a row with the donut (8/4), no breathing room; KPI cards cramped/overlapping (WhatsApp Sent text touching card above). | MEDIUM | Old 12-col grid with timeline+donut combined; funnel misplaced; KPI grids lacked vertical gap; trend chips could wrap/collide. | Row1 = Outcome Distribution + Sales Funnel side-by-side (lg:grid-cols-2, 400px cards); Row2 = Engagement Timeline full width; Row3 = Hourly Distribution full width. KPI grids get gap-y-6; primary cards gap-2 + leading-tight + shrink-0 nowrap trend chips; secondary cards min-h-[92px]. Verified headless: all 3 charts draw, headings in order, no overlap. | index.html, app.js | ~30-60 min | FIXED | 2026-08-14 (round 5: dialing status / source filter / layout / trends / watchdog runner)
57 | Frontend / KPIs | KPI trending % stopped showing after switching to real deltas — freshly uploaded leads have no called_at so trends showed '—' forever. | MEDIUM | _computeKpiTrends only used called_at_iso/called_at; leads without a call have neither. | Timestamp resolution now called_at_iso ?? called_at ?? created_at (API epoch-seconds, normalized) ?? created_at_iso ?? added_at; no-baseline returns 0% trending_flat (never '—'); conversion trend computed as relative delta of interested/called rate per window. Unit-verified: +225% with creation-time fallback. | app.js | ~30-60 min | FIXED | 2026-08-14 (round 5: dialing status / source filter / layout / trends / watchdog runner)
58 | Ops / Watchdog | Watchdog cron job failed: script executed via WSL2 (broken on this machine: ext4.vhdx missing) and CRLF line endings broke the remote bash; cron also inherited an unsupported model. | HIGH | Runner was a .sh script executed through WSL2; heredoc pipe translated LF→CRLF. | Replaced with hermes_watchdog_runner.py (Python subprocess, bytes piped with text=False so LF preserved); queue-stuck detection now counts recent completed jobs (flowing-but-large queues like 560 jobs are NOT stuck); cron updated to the Python runner. Live check now correctly reports only glitch=burst (Gemini 429) while queue flows. | watchdog/hermes_watchdog_runner.py, hermes_watchdog_check.sh, cron fae943a17488 | ~30-60 min | FIXED | 2026-08-14 (round 5: dialing status / source filter / layout / trends / watchdog runner)
59 | Voice / Greeting | Pre-recorded greeting audio never played on calls — GEMINI_LIVE_FIRST_OPENING=true skipped it entirely, and the greeting PCM loader rejected freshly-captured audio (text-hash mismatch) forcing a regeneration loop. | HIGH | GEMINI_LIVE_FIRST_OPENING=true in VPS .env made the session wait for Gemini Live to speak first (silent on 429); ensure_opening_pcm primed with the campaign opening text (80 chars incl. project name) while the WS session loaded the template greeting (71 chars) -> hash mismatch -> greeting discarded every call. | Flipped GEMINI_LIVE_FIRST_OPENING=false (pre-recorded plays first); ensure_opening_pcm now uses the canonical resolved_greeting_text so capture + playback hashes match; load_recorded_greeting_pcm tolerates fresh captures (<7d, gemini_live_capture/edge_tts source) with a hash mismatch; Smooth Calls baseline updated to expect false. Live-verified: greeting 5.05s loads, Gemini Live connects in background during playback, S2S answered with 29 audio chunks. | backend/core/greeting_pcm.py, backend/services/vobiz_bridge/live_session.py, VPS .env, smooth_calls_baseline.json, tests | ~30-60 min | FIXED | 2026-08-14 (round 6: greeting audio flow / transcription model / language config / transcript labels)
60 | Transcription | Call transcription not generating — configured model gemini-2.5-flash is deprecated/unavailable for new keys (404 on every request). | HIGH | All analysis/transcription paths defaulted to gemini-2.5-flash (config.py, console_api.py, transcriber.py, worker.py, gemini_analyzer.py, call_analyzer.py, whatsapp_conversation.py); Google removed it for new API keys. | Switched every default to gemini-3.1-flash-lite (verified working: REST probe returned OK; S2S returned 29 audio chunks). Updated VPS .env GEMINI_TRANSCRIPTION_MODEL. Zero gemini-2.5 references remain in code. | backend/config.py, api/routes/console_api.py, services/transcriber.py, core/worker.py, services/gemini_analyzer.py, services/call_analyzer.py, services/whatsapp_conversation.py, VPS .env | ~30-60 min | FIXED | 2026-08-14 (round 6: greeting audio flow / transcription model / language config / transcript labels)
61 | Frontend / Config | No UI to configure pre-recorded greeting audio, primary language (Telugu) or multilingual mirroring — the user's Configuration page needs plug-and-play voice controls that reflect to the backend instantly. | MEDIUM | Language was only set via GEMINI_LIVE_LANGUAGE env; greeting audio had no status/record UI. | New Voice & Language card in Configuration: Pre-recorded Greeting Audio status + Record Greeting button (POST /api/tuning/record-greeting, Gemini Live call voice); Primary Language dropdown (te-IN default, en/hi/kn/ta) + multilingual mirroring toggle; GET /api/greeting/status endpoint; language+mirror persisted in role_state.vobiz_config via /api/tuning; live session resolves via resolved_live_language() and injects [LANGUAGE] instructions into the system prompt + languageCode into Gemini Live setup. VPS set to te-IN + mirror ON. | index.html, app.js, backend/api/routes/console_api.py, backend/core/state.py, backend/services/vobiz_bridge/live_session.py | ~30-60 min | FIXED | 2026-08-14 (round 6: greeting audio flow / transcription model / language config / transcript labels)
62 | Frontend / Transcript | Transcript modal used fake SoundHelix demo MP3s as recordings, and speaker bubbles showed 'AI Assistant' instead of the agent name. | MEDIUM | openTranscriptModal hard-coded leadId%2 ? SoundHelix-Song-1 : Song-2 for the audio player; sender label hard-coded 'AI Assistant'. | Recording player now uses lead.recording_url/path (no fake audio); sender shows 'Vernika' for agent turns; transcript parser accepts agent-name/user labels (Vernika:, user:) and maps AGENT/CUSTOMER legacy labels; transcription prompt asks for {agent_name} + user speaker labels. | app.js, backend/api/routes/console_api.py, backend/services/transcriber.py | ~30-60 min | FIXED | 2026-08-14 (round 6: greeting audio flow / transcription model / language config / transcript labels)
63 | Flow | Prompt/RAG/greeting changes in the frontend must reach the live call — verified the full chain and closed the loop (DB wins, cache invalidated on save, files mirrored). | MEDIUM | Historical confusion between file prompt (packaged) and DB prompt (console edits) — resolved prompt prefers DB, falls back to file; KV cache (10-min TTL) invalidated on every tuning save. | Verified live: POST /api/tuning updates role_state + mirrors files + invalidates caches; build_role_system_prompt reads DB-first; same system prompt serves manual calls and campaign calls (both via handle_vobiz_ws_live). | backend (verified), no code change needed | ~30-60 min | VERIFIED | 2026-08-14 (round 6: greeting audio flow / transcription model / language config / transcript labels)

## Data Source & Retake
Feature Change | Requirement | Implementation | Files | Status
Data Source column | Leads table shows which Excel/CSV file each call came from (cold vs digital) | Added <th>Data Source</th> + dataSourceCellHtml(r) reading r.source_file/segment/extra.upload_source with Cold/Digital badge; _SLIM_LEAD_KEYS includes source_file+segment; search matches source | frontend/templates/console.html, frontend/static/js/campaign.js, backend/core/campaign_payload.py | DONE
Retake label | Sandbox 1 = no retake (Original call); Sandbox 2 = 'Retake 2' (2nd call), 'Retake 3' (3rd call) | retake_label = 'Original call' when retries==0, 'Retake {attempt_num}' when >0 (removed '/max' format) | backend/core/campaign_payload.py | DONE
Sandbox 1 isolation | Cold calling (P1/P2) vs digital leads (P3) isolated within Sandbox 1; digital watchdog dials P3 immediately | Legacy worker source guard skips digital; orchestrator routes digital->P3; excel/sheets/webhook watchdogs queue FRESH_CALL source=digital; .env checklist for distinct P1/P2/P3 | backend/core/worker.py, number_allocator.py, digital_excel_ingest.py, google_sheets_ingest.py, api/routes/campaign.py | DONE
Clear Data button | Remove-all-data button next to Start/Stop Campaign | 'Clear Data' in console (executeWipe) + root dashboard Quick Actions (campaignControlClear) - full wipe via POST /api/campaign/wipe incl. memory/messages/site-visits/files | frontend/templates/console.html, frontend/static/js/restored.js, app.js, backend/api/routes/campaign.py, backend/core/storage.py | DONE
KPI click-through | Clicking any KPI card opens the underlying leads | All 16 console .stat-cards -> openStatDetail; all 8 root KPI cards -> openKpiModal (added avg_rating + inbound_interest branches) | frontend/templates/console.html, index.html, kpi_modal.js | DONE
Single prompt/RAG/audio | All sandboxes run on ONE prompt + ONE RAG + ONE prerecorded audio | prompts/sales_1_prompt.txt + data/sales_1/rag_source.txt + data/greetings/greeting_sales_1.pcm; role_prompts.py falls back to sales_1 for any role | backend/prompts/, backend/data/sales_1/, backend/data/greetings/, backend/prompts/role_prompts.py | DONE

## Final Verification
Check | Result | Evidence / Notes
Backend core compile (38 files) | PASS 38/38 | py_compile all core modules clean
Backend services + API compile/import (96 files) | PASS 96/96 | clean subprocess import, zero exceptions
Frontend JS parse (10 files) | PASS 10/10 | node --check all JS clean
HTML inline scripts (5 files) | PASS 5/5 | vm.Script parse clean
Frontend asset references | PASS 13/13 | all scripts/css exist
Frontend flow wiring (9 flows) | PASS 9/9 | upload/list/start/stop/wipe/KPI/tuning/transcript/recording
VPS endpoints | PASS all 200 | health, state, sources, leads, manifest, console, root
VPS containers | PASS all healthy | backend, postgres, openwa, caddy
VPS health agents | PASS 10/10 ok, 0 issues | smooth_calls, config, concurrency, callback, rag, media, campaign, schedule, integration, call_quality
Vobiz answer probe | PASS | XML <Stream> -> wss://.../ws/vobiz
Legacy token sweep | PASS 0 hits | no sales_2/channel_partner/surya/data-edge/pitchx/priya
Secrets excluded from git | PASS | .gitignore blocks .env, data, venv, openwa, brochures
Watchdog (VPS) | PASS | timer active, service exits 0, TICK every 60s
Campaign stopped | PASS | active=false, active_calls=0, dialing=0, 8 pending leads untouched